## MOM
Trustea
MOM |  | Minutes of the Meeting- Sinha & Co. |  | Date | 2024-02-16
Project Name |  | Integrated Billing & Financial System(2022-2023) | Project Number |  | 1
Participants |  | Avijit Paul, Indranil Bannerjee, Surajit Naskar, Anindita Biswas, Sylvester Rajesh Mondal | Discussions
Remarks |  |  | Deliverables |  | Sinha & Co.
Sl No. | Points Discussed
1 | Arrange Four action icons in one row.
2 | Pagination button must work properly.
3 | Remove all horizontal scroll bar.
4 | In Miscellaneous Letters menu, remove Subject and reference column from table to avoid horizontal scroll bar.
5 | In Client Address menu, country field must be non-mandatory.
6 | After close of the web-application, user must logout automatically.
7 | In client address and Client Attention menus, copy functionality must work properly.
8 | Add Client Attention form in 'New Client' module.
9 | New Client', 'Client Name', 'Client Address' and 'Client Attention' module need to be grouped in a single sub-module.
10 | In Master module, Department and Designation menu must be working properly.
11 | In Master module, icon location must be changed in Code Master menu.
12 | Create Delete log file of all menus in Admin module. (As discussed over the phone, log file will be implemented after confirmation from Avijit Sir.)
13 | In Client Name menu, on creating a new client need to check for same name exist or not. If exist give a pop-up.
14 | In MIS module, Matter Status (latest) and Matter Status menu to be merged.
15 | In Payment (Voucher) menu, remove Service tax field and add GST field.
16 | In Payment (Voucher) menu, design issue in Print functionality to be rectified.
17 | In Payment (Voucher) menu, Delete Message issue.
18 | In Voucher all menus, lookup data fetch by 'Payee Type' data and with selected Other option need an input field beside 'Payee Type' field.
19 | In all Report (Print) and letter (Print) part, text size must be 11px. And reduce the height and padding.
20 | In Receipt Voucher (Client) menu, remove Service tax field.
21 | In Receipt (Bill Adjustment-Client) menu, remove lookup from 'Bill number' and 'Matter' field. Matter code fetch by Bill number.
22 | In 'Adjustment (Normal)' menu, Print functionality must work properly.
23 | In 'Finance' module, Check-print functionality must work properly.
24 | In 'Advance Adjustment (Counsels/Clerk/Arbitrator/Steno)' menu, Advance amount must be fetched by selecting the payee name. Voucher date must be current date.
25 | In 'Advance Transfer JV' menu, Matter code must be fetched by Client code.
26 | In 'Advance Adjustment JV (Client-Bill)' menu, 'Advance' field lookup fetch all data of Advance, Settled, Balance, Adjusted Now fields.
27 | Remove background colour from all Print pages.
28 | All PDF must be open in a New tab.
29 | Add 'Sinha' logo in all Letter, PDF and Report part.
9, 12 - These are new requirements.